## Sheet1
Project_ID | Implementation_By | Project | Scope | HO_Date | Site_ID | Site_Name | New_RAT | Site_Engineer | Sub_Contractor | Site_Status | Responsible | Civil_PAT_Date | SAQ_Clearance_Date | Approval_Received_Date | MCW_Requested_Date | MCW_Completed_Date | Mobilization_Status | Mobilized_Date | Installation_Status | Installation_Date | Power_Connected_Date | TX_Connected_Date | Commissioning_Status | Commisioned_Date | SAR_Status | SAR_Date | PAT_Status | PAT_Pass_Date | Check_List_Submitted | Check_List_Verified | On_Air_Target | On_Air_Status | On_Air_Date | PR_Submitted_for_TSS | PR_Raised_for_TSS | PR_Number_for_TSS | TSS_PO_number | PO_Issued_for_TSS | TSS_HO | TSSR_Submitted | TSSR_Approved | BOQ_Submitted | Imp_HO | PR_Submission_for_Imp | PR_Number_for_Imp | PR_Raised_for_Imp | PO_Issued_for_Imp | PR_Sub_for_supply | PR_Number_for_supply | PR_Raised_for_supply | PO_Issued_for_supply | PI_Submitted | PI_Number | PI_Approved | TRC_Completed | BOI_Completed | ICL_Completed | LC_Issued | Shipped | Received_at_port | Delivered_to_WH | Reconciled | COW_Submitted | COW_Approved | Supply_HW_PAC_Submitted | Supply_HW_PAC_Approved | Imp_PAC_Submitted | Imp_PAC_Approved | Supply_SW_PAC_Submitted | Supply_SW_PAC_Approved | Capitalization_Supply_HW | Capitalization_Imp | Capitalization_Supply_SW
Example Data | Huawei | Covid 19 Capacity Update 3 | Additional BB Card installation | 2021-06-24 | BDAMB1 | BDAMB1 | Not Available | Shehan | L&H | On Air | Not Apllicable | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | 2021-08-30 | Completed | 2021-08-30 | Completed | 2021-08-30 | 2021-08-31 | 2021-09-01 | Completed | 2021-08-30 | Not Available |  | Pass | 2021-09-07 | 2021-09-08 | 2021-09-09 |  | Completed | 2021-09-07 | 2021-09-08 | 2021-09-09 |  |  | 2021-09-12 |  | 2021-09-14 | 2021-09-15 | 2021-09-16 | 2021-09-17 | 2021-09-18 |  | 2021-09-20 | 2021-09-21 | 2021-09-22 |  | 2021-09-24 | 2021-09-25 | 2021-09-26 |  | 2021-09-28 | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-02 | 2021-10-03 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-16 | 2021-10-17